## Cover
SSCN
SEG2.2
From BMH ADL to BU ADL
CABLE ROUTE STUDY
| ISSUE: |  | DATE:
| CRS02 |  | 2023-10-19
AUTHORISATION
|  | NAME | DATE
ORIGINATOR |  | George BARLOW | 2023-10-19
Mark JONKERGOUW
Alcatel Submarine Networks - Confidential - © 2023

## RPL Abbreviations
Abbreviation | Meaning | Typical Use
ABxx | As-Built | AB01
AC | Alter Course | AC1
AF | As Found (Cable) | CX IS AF CABLE 1
ALxx | As-Laid | AL01
AP | Articulated Pipe | AP START
BA | Beach Allowance | BA 50m
BMH | Beach ManHole | BMH PORTH CURNO
BU-xxx | Branching Unit | BU-1 (ABJ)
CA | Cable Allowance (Beach/Final Splice) | CABLE ALLOWANCE
CB | Concession Block | CB ENTER SHELL B2
CBC (HG) | Change in Burial Conditions - Hardground Layer within Target Burial | CBC (HG)
CBC (HT) | Change in Burial Conditions- High Tensions possible - Stiff/Dense Sediments | CBC (HT)
CBC (SB) | Change in Burial Conditions -Seabed Features (Boulders, Pockmarks etc) | CBC (SB)
CBC (SC) | Change in Burial Conditions -Strong Currents | CBC (SC)
CBC (SL) | Change in Burial Conditions -Marginal Slopes | CBC (SL)
CBC (SR) | Change in Burial Conditions -Subcropping Rock within Target Burial | CBC (SR)
CBC (SS) | Change in Burial Conditions - Soft sediment - Potential Plough Run Away | CBC (SS)
CBC (UXO) | Change in Burial Conditions – Burial where UXO Risk has been sufficiently mitigated to allow burial operations. | CBC (UXO)
CC | Cable Corridor | CC ENTER
CRE | Cable route Estimate | CRE01
CRS | Cable Route Study | CRS01
CT | Comment | CT ENTER SOFT SEDIMENT
CX | Cable Crossing | CX IS CABLE 1
CZ | Contiguous Zone | MB CZ ISO/EZ ISO
DA | Double Armour | DA-14
DE | Duct End | DE
DIS | Disputed Maritime Boundary | MB TW ISO/EZ DIS
DOB | Depth of Burial | DOB 1m
DS | Duct start | DS
DTS | Desk Top Study | See "CRS"
EA | Earth Plate | EA SEA EARTH PLATE
EOB | End of burial | PLUP EOB
EZ / EEZ | Exclusive Economic Zone | MB EZ ISO/CZ ISO
FS | Final Splice | FS-ISN-001/FS FINAL SPLICE
FZ | Fishing Zone | MB FZ ISO/TW ISO
IS | In Service | CX IS CABLE 1
IS | Initial Splice | IS-IBZ-001/IS INITIAL SPLICE
JB | Joint Box | JB 1002AB-1
KP | Kilometre Point | KP 1521.222
LC | Land Cable | LC
LP | Landing Point | LP PORTH CURNO
LW | Lightweight | LW-17
LWP | Lightweight Protected | LWP-17
MB | Maritime Boundary | MB TW ISO/EZ ISO
MDA | Medium Double Armour | MDA-17
OCB | Oil Concession Block | OCB RC31- ENTER
OOS | Out of Service | CX OOS CABLE 1
PLB | Post Lay Burial | PLB START
PLDN | Plough Down | PLDN
PLI | Post-Lay Inspection | PLI START
PLIB | Post Lay Inspection and Burial | PLIB START
PLN | Planned cable | CX PLN CABLE 1
PLUP | Plough Up | PLUP
PL-xxx | Post Load | PL01
PLSE | Pre Laid Shore End | PLSE
POL | Point On Line | POL
PSR-xxx | Post Survey Route | PSR01
PTEQ/TEQ | Passive Tilt Equaliser | PTEQ-01101
PX | Pipeline Crossing | PX PIPELINE 1
REH | Route Engineering Handbook | REH
RNB (HG) | Risk of Non-Burial - Hardground Layer within Target Burial | RNB (HG)
RNB (HT) | Risk of Non-Burial - High Tensions possible - Stiff/Dense Sediments | RNB (HT)
RNB (SB) | Risk of Non-Burial -Seabed Features (Boulders, Pockmarks etc) | RNB (SB)
RNB (SC) | Risk of Non-Burial -Strong Currents | RNB (SC)
RNB (SL) | Risk of Non-Burial -Marginal Slopes | RNB (SL)
RNB (SR) | Risk of Non-Burial -Subcropping Rock within Target Burial | RNB (SR)
RNB (SS) | Risk of Non-Burial - Soft sediment - Potential Plough Run Away | RNB (SS)
RNB (UXO) | Risk of Non-Burial – Burial where UXO Risk has been sufficiently mitigated to allow burial operations. | RNB (UXO)
ROADM
RPL | Route Position List | RPL
R-xxx /RPTR | Repeater | R01101
SA | Single Armour | SA-14
SAH | Single Armour Heavy | TR LWP-17/SAH-20
SAL | Single Armour Light | SAL-17
SC | Slack Change | SC 3%
SEQ-xxx | Shape Equaliser | SEQ-001
SEU | Sea Earth Unit | SEU
SJ-YYY-xxx | Ship Joint | SJ-ISN-001
SLD | Straight Line Diagram | SLD
SOB | Start of burial | PLDN SOB
SRxx | Survey Route | SR01
SSE | Separate Shore End | SSE
ST | Seabed Temperature | ST 15
TEQ-xxx | Tilt Equaliser | TEQ-01101
TR | Transition | TR LWP-17/LW-17
TS | Terminal Station | TS PORTH CURNO
TW | Territorial Waters | MB TW ISO/CZ ISO
UXO | Unexploded Ornance | Enter UXO Zone
WD | Water Depth | WD 2300m
Note on C27: Alcatel: Code is three letter ident for ship, eg "ISN" for Ile de Sein. Number (001) is incremented joint number made by ship.
Note on C30: Alcatel: Code is three letter ident for ship, eg "ISN" for Ile de Sein. Number (001) is incremented joint number made by ship.
Note on C71: Alcatel: Code is a three letter code to identify the ship, eg ISN for Ile de Sein.

## Check List
RPL CHECKLIST
ACTIONS | YES | NO | DATE | RPL ISSUE | COMMENTS
1. CRS Routes Risk Review (ASN) - Routes Approved |  | ü
2. CRS Routes Approved for Survey (Client) |  | ü
3. Survey Routes and Notifications Issued to UKHO ,ICPC & GMCD |  | ü
4. Major Route Changes since UKHO, ICPC & GMCD Pre-Survey? (If Yes consider re-issuing Notifications) |  | ü
5. Survey Routes Issued to Survey Contractor |  | ü
6. Internal Post Survey Route Risk Review Conducted |  | ü
7. Client Post Survey Review Conducted |  | ü
8. Client Aligned with ASN Recommendations (If No - See Change List for Details) |  | ü
9. Client RPL Approval for Route (Route Fixed, SLD tbc) |  | ü
10. Client Approval for Articulated Pipe Quantity |  | ü
11. Cable Bodies Added |  | ü
12. Separation for Cable Bodies Approved (CX/PX etc.) |  | ü
13. Client RPL Approval for SLD (SLD Ready to Manufacture, RPTRs & Cable Types Fixed)) |  | ü
14. Crossing Notifications Prepared and on SDMS |  | ü
15. Plough Review Conducted (If Route Change Proposed Inform Project Team) |  | ü
16. Has Route Been Adjusted Since Fixed (Inform Project Team and List CXs Affected - Reissue CX Notifications) |  | ü
17. As Built SLD Received |  | ü
18. As Built RPLs to Installer |  | ü
19. Post Load SLD/Cable Change Diagrams Received |  | ü
20. Post Load RPLs to Installer |  | ü
21. As Laid Routes Approved |  | ü
22. As Laid Routes Uploaded to SDMS |  | ü
23. As Laid Routes Issued to UKHO & GMCD |  | ü
ISSUE No
GMCD Issue No | 99

## Change List
RPL / SLD & Route Engineering - CHANGES & TRACKING SHEET
ISSUE | DATE | Length |  | CHANGE
CRS02 | 2023-10-19 | Route length: | 391.7716 | First Cable Route Study (CRS) version of the route created by ASN ASN Route optimisations made at this stage without full visibility of the OMS/FUGRO Desktop Study "Label" depths are taken from the Maritime charts to indicate extent of depth related events (burial etc) "Depth" depths are computed using GMRT bathymetry datasets. There may be mis-matches from the "Label" depths Plough events included but do not account for planned skips due to crossings etc. Sebed temperatures included. HDD Exit positions are indicative at this stage. To be confirmed.
|  | Cable Length: | 395.9093
RPL Chronology Sequence Summary
CRE |  | Cable Route Estimate RPLs
CRS |  | Cable Study Routes RPLs
SR |  | Survey Route RPLs
PSR |  | Post Survey Route RPLs
_R |  | RPL Fixed
_S |  | SLD Fixed
_RS |  | RPL and SLD Fixed
_AC_ONLY |  | RPL stripped of all data except Alter Courses
AB |  | As-Built RPLs
PL |  | Post Load RPLs
AL |  | As-Laid RPLs

## RPL
Point N° | Label | Latitude (WGS 84) |  |  | Longitude (WGS 84) |  |  | A/C | Brg (°) | Alter Course (- P + S) | Depth (m) | Leg Dist (km) | Cum KP Dist (km) | Reverse KP Dist (km) | Cable Type | Surface Slack (%) | Leg Cable (km) | Cum Cable (km) | Cable by Type (km) | Bottom Slack (%) | Reverse Cable Dist (km)
0 | BU GDI | 34 | 57.561 | S | 138 | 30.442 | E |  | 256.8503 |  | 5 |  | 0 | 391.772 |  |  |  | 0 | 0 |  | 395.909
[12 empty] | 0 |  |  | SAL-17 | 0 | 0.05 |  |  | 0
1 | CABLE ALLOWANCE 50M | 34 | 57.561 | S | 138 | 30.442 | E |  | 256.8503 |  | 5 |  | 0 | 0 |  |  |  | 0.05 |  |  | 0
[12 empty] | 1.0343 |  |  | SAL-17 | 0.5001 | 1.0395 |  |  | 0.5
2 | TR SAL-17/MDA-17 | 34 | 57.6883 | S | 138 | 29.7803 | E |  | 256.8503 |  | 6.0376 |  | 1.034 | 390.738 |  |  |  | 1.089 | 1.089 |  | 394.82
[12 empty] | 0.0228 |  |  | MDA-17 | 0.5003 | 0.0229 |  |  | 0.5
3 | HDD EXIT | 34 | 57.6911 | S | 138 | 29.7658 | E |  | 256.8503 |  | 6.0921 |  | 1.057 | 390.715 |  |  |  | 1.112 |  |  | 394.797
[12 empty] | 4.1683 |  |  | MDA-17 | 0.5002 | 4.1891 |  |  | 0.5
4 | PLUP; WD 15m | 34 | 58.2039 | S | 138 | 27.0991 | E |  | 256.8503 |  | 15.0256 |  | 5.225 | 386.547 |  |  |  | 5.301 |  |  | 390.608
[12 empty] | 2.4634 |  |  | MDA-17 | 0.5 | 2.4757 |  |  | 0.5
5 | AC | 34 | 58.507 | S | 138 | 25.523 | E | AC | 250.1341 | -6.7 | 16.754 |  | 7.689 | 384.083 |  |  |  | 7.777 |  |  | 388.132
[12 empty] | 0.9551 |  |  | MDA-17 | 0.5 | 0.9598 |  |  | 0.5
6 | TR MDA-17/SAL-17 | 34 | 58.6825 | S | 138 | 24.9328 | E |  | 250.1341 |  | 17.4241 |  | 8.644 | 383.128 |  |  |  | 8.737 | 7.648 |  | 387.172
[12 empty] | 0.7861 |  |  | SAL-17 | 0.5 | 0.79 |  |  | 0.5
7 | AC | 34 | 58.827 | S | 138 | 24.447 | E | AC | 241.1256 | -9 | 17.9756 |  | 9.43 | 382.342 |  |  |  | 9.527 |  |  | 386.382
[12 empty] | 1.1487 |  |  | SAL-17 | 0.5 | 1.1545 |  |  | 0.5
8 | AC | 34 | 59.127 | S | 138 | 23.786 | E | AC | 226.1325 | -15 | 18.7815 |  | 10.579 | 381.193 |  |  |  | 10.681 |  |  | 385.228
[12 empty] | 2.8176 |  |  | SAL-17 | 0.5 | 2.8317 |  |  | 0.5
9 | AC | 35 | 0.183 | S | 138 | 22.451 | E | AC | 221.2938 | -4.8 | 20.5229 |  | 13.396 | 378.376 |  |  |  | 13.513 |  |  | 382.396
[12 empty] | 36.1277 |  |  | SAL-17 | 0.5 | 36.3084 |  |  | 0.5
10 | AC | 35 | 14.863 | S | 138 | 6.757 | E | AC | 235.5459 | 14.3 | 38 |  | 49.524 | 342.248 |  |  |  | 49.821 |  |  | 346.088
[12 empty] | 12.4821 |  |  | SAL-17 | 0.5 | 12.5445 |  |  | 0.5
11 | AC | 35 | 18.682 | S | 137 | 59.969 | E | AC | 248.795 | 13.2 | 33 |  | 62.006 | 329.766 |  |  |  | 62.366 |  |  | 333.543
[12 empty] | 2.9985 |  |  | SAL-17 | 0.5 | 3.0135 |  |  | 0.5
12 | ST 18 | 35 | 19.2685 | S | 137 | 58.1245 | E |  | 248.795 |  | 32.8565 |  | 65.004 | 326.768 |  |  |  | 65.38 |  |  | 330.529
[12 empty] | 15.0782 |  |  | SAL-17 | 0.5 | 15.1536 |  |  | 0.5
13 | AC | 35 | 22.218 | S | 137 | 48.846 | E | AC | 252.394 | 3.6 | 32.135 |  | 80.083 | 311.689 |  |  |  | 80.533 |  |  | 315.376
[12 empty] | 58.905 |  |  | SAL-17 | 0.5 | 59.1996 |  |  | 0.5
14 | AC | 35 | 31.8532 | S | 137 | 11.739 | E | AC | 269.6151 | 17.2 | 34.4224 |  | 138.988 | 252.784 |  |  |  | 139.733 |  |  | 256.176
[12 empty] | 0.4764 |  |  | SAL-17 | 0.5 | 0.4788 |  |  | 0.5
15 | MPA ENTER Southerm Spencer Gulf | 35 | 31.855 | S | 137 | 11.4239 | E |  | 269.6151 |  | 34.6401 |  | 139.464 | 252.308 |  |  |  | 140.211 |  |  | 255.698
[12 empty] | 6.7974 |  |  | SAL-17 | 0.5 | 6.8314 |  |  | 0.5
16 | CX OOS TELE Perth (Cottesloe)-Adelaide XA = 19 | 35 | 31.8796 | S | 137 | 6.927 | E |  | 269.6151 |  | 40 |  | 146.262 | 245.51 |  |  |  | 147.043 |  |  | 248.866
[12 empty] | 23.464 |  |  | SAL-17 | 0.5001 | 23.5814 |  |  | 0.5
17 | ST 17 | 35 | 31.9649 | S | 136 | 51.4043 | E |  | 269.6151 |  | 59.2156 |  | 169.726 | 222.046 |  |  |  | 170.624 |  |  | 225.285
[12 empty] | 6.8393 |  |  | SAL-17 | 0.5001 | 6.8735 |  |  | 0.5
18 | MPA EXIT Southerm Spencer Gulf | 35 | 31.9897 | S | 136 | 46.8796 | E |  | 269.6151 |  | 69.1091 |  | 176.565 | 215.207 |  |  |  | 177.498 |  |  | 218.411
[12 empty] | 1.3077 |  |  | SAL-17 | 0.5001 | 1.3143 |  |  | 0.5
19 | AC | 35 | 31.9945 | S | 136 | 46.0145 | E | AC | 258.3903 | -11.2 | 70.6043 |  | 177.873 | 213.899 |  |  |  | 178.812 |  |  | 217.097
[12 empty] | 1.4917 |  |  | SAL-17 | 0.5001 | 1.4992 |  |  | 0.5
20 | ST 16 | 35 | 32.1568 | S | 136 | 45.0478 | E |  | 258.3903 |  | 72.3914 |  | 179.364 | 212.408 |  |  |  | 180.311 |  |  | 215.598
[12 empty] | 57.4332 |  |  | SAL-17 | 0.5 | 57.7204 |  |  | 0.5
21 | AC | 35 | 38.4072 | S | 136 | 7.8031 | E | AC | 241.2322 | -17.2 | 115 |  | 236.798 | 154.974 |  |  |  | 238.032 |  |  | 157.877
[12 empty] | 7.2554 |  |  | SAL-17 | 0.5 | 7.2917 |  |  | 0.5
22 | AC | 35 | 40.2954 | S | 136 | 3.5891 | E | AC | 219.9444 | -21.3 | 115 |  | 244.053 | 147.719 |  |  |  | 245.323 |  |  | 150.586
[12 empty] | 3.688 |  |  | SAL-17 | 0.5002 | 3.7064 |  |  | 0.5
23 | MB TW AUS / CZ AUS / | 35 | 41.8244 | S | 136 | 2.0196 | E |  | 219.9444 |  | 120 |  | 247.741 | 144.031 |  |  |  | 249.03 |  |  | 146.879
[12 empty] | 0.2185 |  |  | SAL-17 | 0.5 | 0.2196 |  |  | 0.5
24 | ST 15 | 35 | 41.915 | S | 136 | 1.9266 | E |  | 219.9444 |  | 120 |  | 247.96 | 143.812 |  |  |  | 249.249 |  |  | 146.66
[12 empty] | 4.4081 |  |  | SAL-17 | 0.5 | 4.4301 |  |  | 0.5
25 | CX OOS TELE Perth (Cottesloe)-Adelaide XA = 42 | 35 | 43.7426 | S | 136 | 0.050006 | E |  | 219.9444 |  | 120 |  | 252.368 | 139.404 |  |  |  | 253.68 |  |  | 142.229
[12 empty] | 11.6569 |  |  | SAL-17 | 0.5002 | 11.7152 |  |  | 0.5
26 | CB EPP 42 ENTER | 35 | 48.5753 | S | 135 | 55.084 | E |  | 219.9444 |  | 137.9903 |  | 264.025 | 127.747 |  |  |  | 265.395 |  |  | 130.514
[12 empty] | 3.9502 |  |  | SAL-17 | 0.5001 | 3.97 |  |  | 0.5
27 | AC | 35 | 50.213 | S | 135 | 53.4 | E | AC | 210.4647 | -9.5 | 142.5881 |  | 267.975 | 123.797 |  |  |  | 269.365 |  |  | 126.544
[12 empty] | 2.5762 |  |  | SAL-17 | 0.5007 | 2.5891 |  |  | 0.5
28 | MB CZ AUS / EZ AUS | 35 | 51.4138 | S | 135 | 52.5325 | E |  | 210.4647 |  | 150 |  | 270.551 | 121.221 |  |  |  | 271.954 |  |  | 123.955
[12 empty] | 10.3047 |  |  | SAL-17 | 0.5 | 10.3563 |  |  | 0.5
29 | ST 14 | 35 | 56.2168 | S | 135 | 49.0603 | E |  | 210.4647 |  | 151.7894 |  | 280.856 | 110.916 |  |  |  | 282.31 |  |  | 113.599
[12 empty] | 4.9226 |  |  | SAL-17 | 0.5001 | 4.9472 |  |  | 0.5
30 | ST 13 | 35 | 58.5111 | S | 135 | 47.4003 | E |  | 210.4647 |  | 158.1209 |  | 285.778 | 105.994 |  |  |  | 287.257 |  |  | 108.652
[12 empty] | 3.7174 |  |  | SAL-17 | 0.503 | 3.7361 |  |  | 0.5
31 | ST 12 | 36 | 0.24377 | S | 135 | 46.1463 | E |  | 210.4647 |  | 180.8234 |  | 289.496 | 102.276 |  |  |  | 290.993 |  |  | 104.916
[12 empty] | 2.4089 |  |  | SAL-17 | 0.5841 | 2.4229 |  |  | 0.5
32 | ST 11 | 36 | 1.3665 | S | 135 | 45.3334 | E |  | 210.4647 |  | 275.9533 |  | 291.905 | 99.867 |  |  |  | 293.416 |  |  | 102.493
[12 empty] | 1.9059 |  |  | SAL-17 | 0.6263 | 1.9179 |  |  | 0.5
33 | ST 10 | 36 | 2.2548 | S | 135 | 44.6901 | E |  | 210.4647 |  | 371.4007 |  | 293.81 | 97.962 |  |  |  | 295.334 |  |  | 100.575
[12 empty] | 1.6248 |  |  | SAL-17 | 0.551 | 1.6338 |  |  | 0.5
34 | ST 9 | 36 | 3.0121 | S | 135 | 44.1416 | E |  | 210.4647 |  | 420.9354 |  | 295.435 | 96.337 |  |  |  | 296.968 |  |  | 98.941
[12 empty] | 1.6095 |  |  | SAL-17 | 0.5446 | 1.6183 |  |  | 0.5
35 | ST 8 | 36 | 3.7623 | S | 135 | 43.5982 | E |  | 210.4647 |  | 466.4126 |  | 297.045 | 94.727 |  |  |  | 298.586 |  |  | 97.323
[12 empty] | 1.513 |  |  | SAL-17 | 1.0066 | 1.5282 |  |  | 0.5
36 | ST 7 | 36 | 4.4675 | S | 135 | 43.0873 | E |  | 210.4647 |  | 610.7241 |  | 298.558 | 93.214 |  |  |  | 300.114 |  |  | 95.795
[12 empty] | 1.5714 |  |  | SAL-17 | 0.7272 | 1.5829 |  |  | 0.5
37 | ST 6 | 36 | 5.1999 | S | 135 | 42.5566 | E |  | 210.4647 |  | 713.5312 |  | 300.129 | 91.643 |  |  |  | 301.697 |  |  | 94.212
[12 empty] | 1.7518 |  |  | SAL-17 | 0.6503 | 1.7631 |  |  | 0.5
38 | ST 5 | 36 | 6.0163 | S | 135 | 41.9648 | E |  | 210.4647 |  | 809.3116 |  | 301.881 | 89.891 |  |  |  | 303.46 |  |  | 92.449
[12 empty] | 2.4101 |  |  | SAL-17 | 0.6211 | 2.4251 |  |  | 0.5
39 | ST 4 | 36 | 7.1396 | S | 135 | 41.1505 | E |  | 210.4647 |  | 927.5633 |  | 304.291 | 87.481 |  |  |  | 305.886 |  |  | 90.023
[12 empty] | 3.1546 |  |  | SAL-17 | 0.6663 | 3.1756 |  |  | 0.5
40 | CB EPP 42 EXIT | 36 | 8.6099 | S | 135 | 40.0845 | E |  | 210.4647 |  | 1108.0456 |  | 307.446 | 84.326 |  |  |  | 309.061 |  |  | 86.848
[12 empty] | 0.8128 |  |  | SAL-17 | 0.9304 | 0.8203 |  |  | 0.5
41 | ST 3 | 36 | 8.9887 | S | 135 | 39.8097 | E |  | 210.4647 |  | 1182.7802 |  | 308.258 | 83.514 |  |  |  | 309.881 |  |  | 86.028
[12 empty] | 1.3796 |  |  | SAL-17 | 1.5232 | 1.4006 |  |  | 0.5
42 | PLDN; WD 1000m | 36 | 9.6317 | S | 135 | 39.3433 | E |  | 210.4647 |  | 1378.8249 |  | 309.638 | 82.134 |  |  |  | 311.282 |  |  | 84.627
[12 empty] | 1.7838 |  |  | SAL-17 | 0.7901 | 1.7979 |  |  | 0.5
43 | WD 1500m | 36 | 10.4631 | S | 135 | 38.7402 | E |  | 210.4647 |  | 1500.0297 |  | 311.422 | 80.35 |  |  |  | 313.08 |  |  | 82.829
[12 empty] | 1.8097 |  |  | SAL-17 | 0.7438 | 1.8232 |  |  | 0.5
44 | TR SAL-17/LWP-17 | 36 | 11.3066 | S | 135 | 38.1282 | E |  | 210.4647 |  | 1625.3182 |  | 313.232 | 78.54 |  |  |  | 314.903 | 306.166 |  | 81.006
[12 empty] | 0.0028 |  |  | LWP-17 | 0.757 | 0.0028 |  |  | 0.5
45 | SC 3.0% | 36 | 11.3079 | S | 135 | 38.1273 | E |  | 210.4647 |  | 1625.5175 |  | 313.234 | 78.538 |  |  |  | 314.906 |  |  | 81.003
[12 empty] | 8.5875 |  |  | LWP-17 | 3.2282 | 8.8648 |  |  | 3
46 | ST 2 | 36 | 15.3102 | S | 135 | 35.2218 | E |  | 210.4647 |  | 2160.2325 |  | 321.822 | 69.95 |  |  |  | 323.771 |  |  | 72.138
[12 empty] | 2.203 |  |  | LWP-17 | 3.9143 | 2.2892 |  |  | 3
47 | AC | 36 | 16.337 | S | 135 | 34.476 | E | AC | 223.4382 | 13 | 2428.6789 |  | 324.025 | 67.747 |  |  |  | 326.06 |  |  | 69.849
[12 empty] | 15.8194 |  |  | LWP-17 | 3.188 | 16.3237 |  |  | 3
48 | AC | 36 | 22.548 | S | 135 | 27.208 | E | AC | 218.6743 | -4.8 | 3385 |  | 339.844 | 51.928 |  |  |  | 342.384 |  |  | 53.525
[12 empty] | 25.0942 |  |  | LWP-17 | 3.1413 | 25.8825 |  |  | 3
49 | AC | 36 | 33.141 | S | 135 | 16.711 | E | AC | 206.3651 | -12.3 | 4700 |  | 364.939 | 26.833 |  |  |  | 368.266 |  |  | 27.643
[12 empty] | 26.833 |  |  | LWP-17 | 3.0186 | 27.643 |  |  | 3
50 | CABLE ALLOWANCE 500M | 36 | 46.14 | S | 135 | 8.714 | E |  | 206.3651 |  | 5210 |  | 391.772 | 0 |  |  |  | 395.909 |  |  | 0
[12 empty] | 0 |  |  | LWP-17 | 0 | 0.5 |  |  | 0
51 | BU ADL | 36 | 46.14 | S | 135 | 8.714 | E |  | 206.3651 |  | 5210 |  | 391.772 | 0 |  |  |  | 396.409 | 81.506 |  | 0
[15 empty] | Cable Type |  |  | Length (km)
[15 empty] | SAL-17 |  |  | 307.2558
[15 empty] | MDA-17 |  |  | 7.6475
[15 empty] | LWP-17 |  |  | 81.506
[15 empty] | Total |  |  | 396.4093

## SLD
Straight Line Diagram
| BU GDI |  | CABLE ALLOWANCE 50M |  | TR SAL-17/MDA-17 |  | PLUP |  | TR MDA-17/SAL-17 |  | PLDN
|  | SAL-17 |  | SAL-17 |  | MDA-17 |  | MDA-17 |  | SAL-17
|  | 0.05 |  | 1.039 |  | 4.212 |  | 3.436 |  | 302.545
| 0 |  | 0.05 |  | 1.089 |  | 5.301 |  | 8.737 |  | 311.282
| 5 |  | 5 |  | 6.0376 |  | 15 |  | 17.4241 |  | 1379
|  |  | TR SAL-17/LWP-17 |  | SC 3.0% |  | CABLE ALLOWANCE 500M |  | BU ADL
|  | SAL-17 |  | LWP-17 |  | LWP-17 |  | LWP-17
|  | 3.621 |  | 0.003 |  | 81.003 |  | 0.5
|  |  | 314.903 |  | 314.906 |  | 395.909 |  | 396.409
|  |  | 1625.3182 |  | 1625.5175 |  | 5210 |  | 5210
| CABLE SUMMARY | [6 empty] | BODIES SUMMARY
| CABLE | SAL-17 | MDA-17 | LWP-17 | TOTAL
| SYSTEM | 307.255 | 7.648 | 81.506 | 396.409
SPARE
| TOTAL | 307.255 | 7.648 | 81.506 | 396.409

## Crossings
Label | Cable Status | Action Needed | Latitude (WGS 84) |  |  | Longitude (WGS 84) |  |  | Depth (m) | Cum KP Dist (km) | Cable Type | Xing Angle (deg)
CX Perth (Cottesloe)-Adelaide XA = 19 (TELE) | OOS | None | 35 | 31.8796 | S | 137 | 6.927 | E | 40 | 146.262 | SAL-17 | 19
CX Perth (Cottesloe)-Adelaide XA = 42 (TELE) | OOS | None | 35 | 43.7426 | S | 136 | 0.050006 | E | 120 | 252.368 | SAL-17 | 42

## Maritime Boundaries
Maritime Boundaries Summary
| BU GDI |  | BU ADL
|  |  |  | TOTAL LENGTH | BODIES SUMMARY
396.409
| 0 |  | 396.409 | 396.409
H-SEAS
TERRITORIAL WATERS
CONTIGUOUS ZONE
ECONOMIC ZONE
INTERNATIONAL WATERS